## Pentest Summary
Test ID | Target Application | Scope | Test Type | Testing Firm | Test Start | Test End | Critical Findings | High Findings | Medium Findings | Low Findings | Informational | Retest Completed | Report Reference | Status
PT-2024-001 | E-Commerce Portal | Authenticated + Unauthenticated Web, API | Black Box + Grey Box | SecureTest Ltd | 2024-09-02 | 2024-09-06 | 0 | 2 | 5 | 8 | 3 | Yes | PT-RPT-2024-001 | Closed – All High remediated
PT-2024-002 | Payments Gateway | Payment flow, API endpoints, 3DS integration | Grey Box | SecureTest Ltd | 2024-10-07 | 2024-10-11 | 1 | 3 | 4 | 6 | 2 | In Progress | PT-RPT-2024-002 | 1 Critical open; retest scheduled
PT-2024-003 | Mobile Customer App | iOS + Android apps, backend APIs | Grey Box | CyberProbe Inc | 2024-11-04 | 2024-11-08 | 0 | 1 | 3 | 7 | 4 | Pending | PT-RPT-2024-003 | Retest scheduled Dec 2024