## CSPM Findings
Finding ID | CSPM Tool | Provider | Account ID | Resource Type | Resource ID | Region | Finding Title | Severity | Category | Benchmark / Standard | Status | Assigned To | Date Identified | Remediation Due | Date Closed | Notes
CSPM-001 | Wiz | AWS | 123456789012 | S3 Bucket | arn:aws:s3:::mcd-data-backup | us-east-1 | S3 Bucket publicly accessible | Critical | Data Exposure | CIS AWS 2.1.5 | Open | DevOps | 2024-11-01 | 2024-11-15 |  | Immediate remediation required
CSPM-002 | Wiz | AWS | 123456789012 | Security Group | sg-0abc123 | us-east-1 | Unrestricted SSH inbound (0.0.0.0/0) | High | Network | CIS AWS 5.2 | In Remediation | Platform Eng | 2024-10-28 | 2024-11-20 |  | Ticket raised DEV-4421
CSPM-003 | Wiz | Azure | sub-0987abcd | Storage Account | st-mcd-dev-01 | eastus | Storage account allows public blob access | High | Data Exposure | CIS Azure 3.5 | Closed | DevOps | 2024-10-10 | 2024-10-31 | 2024-10-30 | Resolved – public access disabled
CSPM-004 | Wiz | GCP | gcp-proj-321 | BigQuery Dataset | analytics_raw | us-central1 | BigQuery dataset is publicly accessible | Critical | Data Exposure | CIS GCP 7.1 | Open | Data Eng | 2024-11-15 | 2024-11-22 |  | Escalated to CISO
CSPM-005 | Wiz | AWS | 234567890123 | IAM Policy | AdminPolicy-v1 | Global | IAM policy grants wildcard (*) permissions | High | IAM | CIS AWS 1.16 | Open | IT Security | 2024-11-18 | 2024-12-05 |  | Least-privilege review needed