## Security Review Process
Review ID | Review Type | Trigger | Scope | Reviewer | Review Date | Decision | Risk Rating | Findings Summary | Remediation Owner | Remediation Due | Status | Reference Doc
CR-2024-001 | Architecture Review | New workload deployment | E-Commerce microservices on EKS | Cloud Security Arch | 2024-09-10 | Approved with conditions | Medium | Missing network segmentation between services | Platform Eng | 2024-10-31 | Closed | ADR-2024-045
CR-2024-002 | Config Baseline Review | Quarterly cycle | All AWS accounts | Cloud Security Eng | 2024-10-15 | Approved | Low | 2 S3 buckets lacking versioning | DevOps | 2024-11-15 | In Progress | CSPM-RPT-Q3-2024
CR-2024-003 | Architecture Review | Major feature release | Payment gateway integration | CISO / Cloud Arch | 2024-11-01 | Conditionally Approved | High | Encryption-at-rest not enforced on RDS | App Security | 2024-11-30 | Open | ADR-2024-052
CR-2024-004 | IaC Template Review | PR raised for prod infra | Terraform modules – networking | Cloud Security Eng | 2024-11-20 | Rejected | High | Publicly accessible security groups | DevOps | 2024-12-05 | Remediation Required | IaC-SCAN-2024-110