## Vulnerability Findings
Finding ID | CVE ID | CVSS Score | Severity | Asset Name | Asset Type | Environment | Owner | Date Identified | Age (Days) | Patch Available | Exploitability (EPSS %) | Remediation Priority | Status | Target Date | Ticket | Notes
VUL-001 | CVE-2024-1234 | 9.8 | Critical | ecomm-api-prod | Container | Production | Platform Eng | 2024-11-01 |  | Yes | 87% | P1 | Open | 2024-11-15 | VUL-TICK-001 | Active exploit in wild
VUL-002 | CVE-2024-5678 | 8.1 | High | payments-svc | Container | Production | Platform Eng | 2024-11-05 |  | Yes | 62% | P2 | In Progress | 2024-11-22 | VUL-TICK-002 | Patch tested in staging
VUL-003 | CVE-2023-9999 | 7.5 | High | vm-dev-mcd-01 | Virtual Machine | Development | DevOps | 2024-10-15 |  | Yes | 45% | P2 | Open | 2024-11-30 | VUL-TICK-003 | Lower env; scheduled patch
VUL-004 | CVE-2024-2222 | 6.5 | Medium | analytics-worker | Container | Production | Data Eng | 2024-11-10 |  | Yes | 30% | P3 | Open | 2024-12-15 | VUL-TICK-004 | No known exploit
VUL-005 | CVE-2023-1111 | 9.0 | Critical | Legacy Batch Host | Virtual Machine | Production | IT Ops | 2024-09-01 |  | No | 75% | P1 | Risk Accepted | 2025-01-15 | VUL-TICK-005 | No patch; compensating controls in place
Formulas:
Age (Days) = TODAY()-DATEVALUE([Date Identified, row below])